## Campaigns
Campaign | Status | Owner | Notes
Repair Red Launch | On Track | Sean (Product Marketing) | Live at all counters as of Monday. First-week gym check-in promo running through Sunday.
Riverside River Cleanup | On Track | Francine (Community) | Saturday event confirmed with Riverside Conservation Group. Volunteer walk-ins, no signup needed.
Cup Compost Rollout — Remaining 15 Cities | Needs Decision | Nick (Sustainability Ops) | Blocked on municipal composting infrastructure in several markets — not solvable by Groundswell alone. Leadership input needed on messaging while incomplete.

## Content Calendar
Date | Asset | Platform | Status
Mon | Email 1 — Why we built Repair Red | Email | Published
Mon | Social Post 1 — Repair Red product photo | Instagram | Published
Wed | Email 2 — Riverside counter closing Saturday | Email | Published
Thu | Social Post 2 — River cleanup announcement | Instagram | Published
Fri | Email 3 — Where your cup actually goes now | Email | Scheduled
Fri | Social Post 3 — Cup/packaging photo | Instagram | Scheduled
Sat | River cleanup event coverage | Instagram Stories | Scheduled

## Blockers
Blocker | Owner | Status
15 of 55 cities still lack commercial composting infrastructure — cup compostability claim can't be made company-wide | Nick (Sustainability Ops) | Open — waiting on city-by-city municipal partnerships, no Groundswell-side fix available
Denver mobile order routing issue flagged by customer complaint (20-min wait, melted order) | Denver Ops Lead | Under investigation